## WASP Well Workovers
Warner ASP - Injectors, Conversions, Reactivations, Completions | [8 empty] | GENERIC PROGRAM for Injectors: | [8 empty] | GENERIC PROGRAM for Producers:
June 26, 2006 | [8 empty] | 1) Soak with 5 m3 of diesel; push into formation with foam pig and water | [8 empty] | 1) Circulate out fill plus scraper
v3.7.1 | [8 empty] | 2) Flow back | [8 empty] | 2) Perf/reperf: 86mm/20 spm/60 deg/24 gm SP
[9 empty] | 3) Remove packer/old tubing string | [8 empty] | 3) Circulate/swab until less than 1% solids
% is wcut unless specified. | [8 empty] | 4) Scrap interval | [8 empty] | 4) Swab to evaluate: If well > 4 m3/hr, RIH pump and PWOP
[9 empty] | 5) RIH coated tbg/packer | [8 empty] | 5) Frac well
[9 empty] | 6) PWOI | [8 empty] | 6) Swab to evaluate; info to Calgary for instructions
Group
|  | Rig | Current |  |  | New Perf Intervals for ASP |  | Work Date Range | mKB | mKB | Existing GLCC Perfs | V/ | Csg | Frac | Current | Life Max | Target | Final
|  | Status | Status |  | Comments | Fr mSS | To mSS | (# days on well) | MD | MD | mKB MD | DIR | Size | History | m3/d | m3/d | m3/d | Results | Notes
Injector Prod Opts
I | 00/08-09 | DONE | Injecting | A |  |  |  | Mar 16-20, 2006 (3) | 988.5 | 992 | 986.5-987.5,988.5-992 | V | 5.5 | Frac'd | 158 | 244 | 150 | $71K 5 m3 diesel; 73mm coated. | 5T Frac if required.
I | 02/09-09 | DONE | Injecting | A |  |  |  | Mar 16-19, 2006 (4) | 986 | 989 | 986-989 | V | 5.5 | Frac'd | 156 | 420 | 150 | $85K 5 m3 diesel; flow 18 m3; 73mm coated. 79red/4grn/14blue/9yel | 5T Frac if required.
I | 00/02-16 | DONE | Injecting | B | Need new W/H. Wrong log PP file. |  |  | Mar 6-15, 2006 (10) | 978 | 986 | 976-986.3 | V | 4.5 | Frac'd | 439 | 500 | 300 | $146K 73mmSH tbg coated. 10 days. No perf/frac. | Perf/Cleanout should suffice.
I | 02/09-20 | DONE | Injecting | C | Static Tubing: 7200 kPa | -58 | -62 | Jun 5-8, 2006 (4) | 984 | 988 | 980-988 | V | 4.5 | No Frac | 732 | 800 | 200 | $110K Circ; Pkr failed to set; 2nd pkr w/60mm coated tbg | DO AFTER 5-21, 16-20 to determine string size.
I | 00/01-29 | DONE | Injecting | D | Needs new W/H. | -65.5 | -73.5 | Mar 21-24, 2006 (4) | 987.5 | 995.5 | 985.1-995.5 | V | 4.5 | No Frac | 142 | 576 | 100 | $115K 5 m3 diesel; flow 8 m3; drill perm pkr; 73mmSH coated | 5T Frac if required.
I | 02/02-29 | DONE | Injecting | D | Needs new W/H. | -66.5 | -72 | Mar 20-22, 2006 (3) | 998.5 | 1004 | 996-1004 | DIR | 5.5 | No Frac | 160 | 620 | 100 | $66K 5 m3 diesel; flow 12 m3; 73mm coated. 2 days. | 5T Frac if required.
I | 04/06-29 | DONE | Injecting | D | Needs new M/V. Old pipe for now. |  |  | Jun 8-24, 2006 (5) | 997 | 1003 | 997-1003 | DIR | 5.5 | Frac'd | 243 | 585 | 100 | $54K 5 m3 diesel; perf 997-1003; 426 m3/d @ 7.5 MPa; coated. | Perf/Cleanout should suffice.
I | 02/10-29 | DONE | Injecting | D |  | -58 | -64 | Mar 23-Apr 17, 06 (5) | 1030 | 1036 | 1024-1031,1033-1035 | DIR | 5.5 | Frac'd | 120 | 140 | 100 | $48K 5 m3 diesel; flow 0.5 m3; Perf 1030-1036; 73mm coated. | Check previous frac size.
I | 03/11-29 | DONE | Injecting | D |  | -66 | -69 | May 25-Jun 4, 06 (6) | 1053 | 1056 | 1052.5-1056 | DIR | 5.5 | Frac'd | 81 | 300 | 100 | $61K 5 m3 diesel; perf 1053-1056; 596 m3/d @ 11 MPa; coated. | Already has coated DEQ, 5T Frac if required.
I | 02/15-29 | DONE | Injecting | D |  | -60 | -64 | Jun 4-7, 2006 (4) | 1077 | 1081 | 1070-1075 | DIR | 5.5 | Frac'd | 54 | 60 | 100 | $57K 5 m3 diesel; perf 1077-1081; 341 m3/d @ 13.5 MPa; coated. | Already has coated DEQ. Check previous frac size.
Conversions (3 P>I, 1 I>P)
I > P | 02/03-16 | RIG ON | - |  | Blocky, Gamma Chatter | -31 | -36 | May 31- in progress | 968 | 973 | 966.2-970.8,973.5-977.8, | V | 4.5 | No Frac | 206 | 440 |  |  | Perf/Cleanout; If < 5 m3/hr, then SOLVENT WASH.
[5 empty] | from 4 Breccia Beds | -38.5 | -43 |  | 975.5 | 980 | 982-986,986.3-991.2
Future work: Aquatrol-1 Wetability Treatment
P > I | 00/11-09 | DONE | Injecting | A |  | -45 | -48.5 | Nov 5-16, 2005 (8) | 987 | 990.5 | 986.9-988.5,990-990.6 | V | 4.5 | Frac'd | 16 | 52 | 150 | $167K 95 m3/d -> 20T -> 138 m3/d @ 14 MPa. Coated 73mm. | 5T Frac if required.
[6 empty] | 52.5 | -54.5 |  | 994.5 | 996.5 |  |  |  |  | (producing rates) |  |  | Appears fluid going to old top perfs. BD=25.3 MPa
P > I | 00/03-16 | DONE | Injecting | A | Original perfs only 7 SPM | -49.5 | -52.5 | Dec 6-14, 2005 (7) | 988 | 991.5 | 988.2-990 | V | 4.5 | Frac'd | 57 | 120 | 300 | $135K After perf: 266 m3/d @ 13 MPa. | Reperf and 5T Frac if required.
[15 empty] | (producing rates) |  |  | Csg integrity poor, but held 14 MPa, got EUB approval.
P > I | 02/05-21 | DONE | Injecting | C |  | -62 | -67 | Feb 6-12, 2006 (6) | 990 | 995 | 989.5-991,992-994 | V | 5.5 | No Frac | 126 | 280 | 200 | $148K 104 Redband Jts. Perf 990-995m. 52 m3/d @ 13.5 MPa. | Perf/Cleanout should suffice.
[15 empty] | (producing rates) |  |  | 10T Frac. BD=24 MPa. 619 m3/d @ 12.5 MPa. Coated 73mm.
Reactivations (1 I Reactivation, 2 P>I Reactivations, 2 P Reentries, 5 Reactivations, 2 I>P Reactivations)
P > I | 02/03-09 | DONE | Injecting | A | 2.5 m sand at 20% poro | -50 | -52 | Sep 23-Oct 16, 05 (9) | 1008 | 1010 | 1002.5-1005 | Dir | 5.5 | Frac'd | 0 | 7 | 150 | $202K 43 m3/d -> 12T -> 158 m3/d @ 14 MPa. Coated 73mm. | 20T Frac likely required.
[6 empty] | -56.5 | -57.5 |  | 1014.5 | 1015.5 |  |  |  |  | (producing rates) |  |  | Fluid going to old top perfs. BD=23.7 MPa. Step Rate test.
P | 02/10-09 | DONE | Prod |  | 10.4 m excellent blocky sand | -39.5 | -40.5 | Mar 1-6, 2006 (4) | 981.5 | 982.5 | 977-978,981-984.5,990-992 | V | 5.5 | No Frac | 0 | 280 |  | $139K Drilled out plugs; Perf 981.5-982.5, 983.5-986.5m | Perf/Cleanout should suffice.
[9 empty] | 983.5 | 986.5 | BPs @ 972 & 988 | [6 empty] | Swab 135 m3/d @ 600m 99%. SG: 4420 kPaa SH89mmPC.
[6 empty] | -41.5 | -44.5 | [10 empty] | 64-1200, 89mm Polycore, 25mm rods w/SH22mm collars | Run 89mm polycore, 25mm rods & pump.
P | 02/14-09 | DONE | Prod |  | REENTRY. 3.6 m blocky sand | -43.5 | -47.5 | Feb 22-27, 2006 (6) | 982.5 | 986.5 | 921.7-922.9, 923.5-925.4, | V | 4.5 | Frac'd | 0 | 115 |  | $168K Drilled out plugs; PT to 10 MPa; Perf 982.5-986.5m. | Perf/Cleanout should suffice.
[5 empty] | Lic Resumption Approval Jan 20 |  |  | May 18-25, 2006 (5) |  |  | 982.6-983.8, 984.4-986.3 | [6 empty] | Swab 108 m3/d @ 720m. Tight spot @ 775m - milled csg. | Get static gradient. Run pump after SG.
SG: 5542 kPa. 32-1200, SH73mm Polycore, 22mmSH.
P | 02/15-09 | DONE | Prod |  | 6.9 m good blocky sand | -41.5 | -45 | Mar 7-10, 2006 (4) | 983.5 | 987 | 981-989 BP @ 976 | V | 5.5 | No Frac | 0 | 170 |  | $125K Drilled out plug; PT to 10 MPa; Perf 983.5-987m. | Perf/Cleanout should suffice.
[11 empty] | Tag bar, no turn on btm | [6 empty] | 144 m3/d, 100%, 570m. 64-1200, 89mmPC, 25mm w/SH22mm | Run 89mm polycore, 25mm rods & pump.
P | 00/06-16 | DONE | Prod |  | regional sand- avoid | -46.5 | -50 | Nov 7-9, 2005 (3) | 984.5 | 988 | 986.3-987.9, 984.5-986.3 | V | 4.5 | Frac'd | 0 | 110 |  | $129K Swabbed 168 m3/d, 99%, 300m. Perf'd only. | Perf/Cleanout should suffice.
32-1200, 73mm Polycore, SH22mm
P | 02/06-16 | N/A | Abn C&C |  | 26.9 m blocky sand- the thickest well | -40.6 | -42.5 |  | 981 | 983 | 969.5-972,973-974.8, | Dir | 5.5 | No Frac | 0 | 22 |  |  | 20T Frac likely required.
|  | Replaced |  |  | Logs had oil shows lower down. | -46 | -48 |  | 987 | 989 | 981-983 CEMBRP | [7 empty] | Do not run pump until ASP ready.
|  | w/Drill |  |  | REMEDIAL CMT on ABANDONMENT | -52 | -56 |  | 993 | 997
I > P | 00/11-16 | DONE | Prod |  | Mostly Blocky | -35 | -42 | May 23-Jun 5 (14) | 970 | 977 | 969.9-972.3, 983.3-987.9 | V | 4.5 | No Frac | 0 | 550 |  | $178K Circ out with coil/diesel twice. Chem cut tbg @ 960m. | Perm Pkr @ 961-965m.
[5 empty] | 2.1 m in top 2 Interbeds | [12 empty] | Circ heavy oil; diesel into perfs; plugs off; repeat 2 times. | Perf/cleanout only. Run pump.
[18 empty] | POOH coated 60mm; RIH 56-1200; 25mm Drive rods. | Future work: Aquatrol-1 Wetability Treatment
I | 00/14-16 | DONE | Injecting | B | 9.3 m good blocky; step rates | -50 | -54 | Sep 7-Oct 16, 05 (9) | 983 | 987 | 977-981.5, 981.5-987.6 | V | 4.5 | No Frac | 0 | 850 | 300 | $162K 475 m3/d @ 7.5 MPa. Coated 73mm tbg. | Perf/Cleanout should suffice.
Step Rate test done.
P > I | 03/16-20 | DONE | Injecting | D | 8.2 m good blocky | -60.5 | -68 | Aug 9-22, 2005 (13) | 984.5 | 992 | 984-985.5 | V | 5.5 | No Frac | 0 | 85 | 200 | $250K Circ to 1004m but BP+cmt @ 998m. 792 m3/d @ 14MPa. | 5T Frac if required.
[8 empty] | Sep 6 & Oct 16, 05 (2) | [6 empty] | (producing rates) |  |  | 20T Frac. BD=42 MPa. Coated 73mm. Step Rate test done.
I > P | 00/04-21 | DONE | Prod |  | 10.2 m good blocky | -44.5 | -49 | May 8-18, 2006 (11) | 975.5 | 980 | 975.7-979, 979.3-983.3 | V | 4.5 | No Frac | 0 | 450 |  | $169K Drill out BP @ 956m. PT to 7 MPa. Work on P.Pkr | No Static Gradient required.
[18 empty] | (6 days). Flowed 29 m3 @ 105 m3/d & 90-95%. | Perf/cleanout only. Run pump.
[18 empty] | SH32-1200, SH73mm, 22mm. Tight spot @ 971m (gone?). | Future work: Aquatrol-1 Wetability Treatment
P | 00/12-21 | DONE | Prod |  | REENTRY. 2.5 m clean but thin | -60.5 | -63.5 | Feb 13-25, 2006 (5) | 986.5 | 989.5 | 986.9-987.6, 988.2-990 | V | 4.5 | Frac'd | 0 | 170 |  | $131K Drilled out plugs; PT to 7 MPa; Perf 986.5-989.5m. | Perf/Cleanout should suffice.
[5 empty] | Lic Resumption Approval Jan 20 | [5 empty] | CEMBRP 974-982 | [6 empty] | SG: 5567 kPa(a). | Get static gradient. Run pump after SG.
Swab 108 m3/d, 97% @ 670m. 56-1200, SH73mm, RP25mm.
P | 02/12-21 | DONE | Prod |  | 15.4 good blocky | -55.9 | -61.2 | Oct 31-Nov 2, 05 (3) | 992 | 996 | 988.0-991.5 (Accumap), | Dir | 5.5 | No Frac | 0 | 290 |  | $146K Swabbed 260 m3/d, 100%, 310m. Perf only. | Perf/Cleanout should suffice.
[8 empty] | Nov 10, 2005 (1) |  |  | (988.2-989.7 ?) | [6 empty] | 64-1200, 89mm Polycore, 25mm rods w/SH22mm collars
P | 03/07-29 | DONE | Prod |  | TVD Log | -60 | -61 | Mar 15-17, 2006 (3) | 1024 | 1025 | 1024-1027, 1028.5-1030 | Dir | 5.5 | Frac'd | 0 | 105 | 100 | $93K SG: 4061 kPa Perf 1024-1025, 1028.5-1030 | First get a static gradient (no tbg/plugs in well)
[5 empty] | (Originally on producing well list) | -63.8 | -65.2 |  | 1028.5 | 1030 | [7 empty] | Swab 34 m3/d, 98% @ 937m. 73mmPC, 22mmSH, 16-1200. | Then perf/cleanout, 73mm polycore & 32-1200
Completions (5 Prod Drills, 2 Inj Drills)
I | 02/13-16 | DONE | Injecting | C | 6) Spud Jan 15 13D-16 $327K | 13D |  | Jan 30-31, 06 (2) | 980 | 987 | Future upper perf potential | V | 5.5 |  |  |  | 300 | $72K Perf 980-987: FL 190m. 763 m3/d @ 6 MPa | Perf/Evaluate/Static Gradient
[5 empty] | Cored | [12 empty] | Ran 101 JTS coated 73mm. Injection into all perfs. | Set up for injection
NOTE ONLY: Pay thickness is 972-987m.
P | 02/7-16 | DONE | Prod |  | 2) Spud Dec 9 7C-16 $311K | 7C |  | Dec 18-20, 2005 (3) | 978 | 983 |  | V | 5.5 |  |  |  |  | $123K Swabbed 256 m3/d, 99.5%, 75m! Perf only. RIH SG. | Perf/Evaluate/Static Gradient only.
[8 empty] | Apr 21-22, 2006 (2) | [9 empty] | SG: 9661 kPaa, 29 deg C. | Do not run pump until ASP ready.
64-1200, 73mm, 25mm rods w/22mm pins
I | 03/7-16 | DONE | Injecting | B | 4) Spud Jan 3 7B-16 $278K | 7B |  | Jan 19-28, 2006 (10) | 983 | 987.5 |  | V | 5.5 |  |  |  | 300 | $183K Perf 983-987.5 (lost gun $35K). 26 m3/d @ 14 MPa | Perf/Evaluate/Static Gradient
[9 empty] | 980 | 983 | [7 empty] | Perf 980-983: FL 100m. 0.5T frac(BD=27.8). 672 m3/d @ 1.4 MPa | Set up for injection
[18 empty] | Rig accidentally ran polycore 73mm, 600 m3/d @ 1.8 MPa | NOTE ONLY: Pay thickness is 980-987.5m.
P | 02/14-16 | DONE | Prod |  | 5) Spud Jan 11 14C-16 $330K | 14C |  | Jan 30-Feb 6, 06 (6) | 971 | 975 |  | V | 5.5 |  |  |  |  | $91K Perf 971-975. Swabbed 43 m3/d @ 15% at 770 m. | Perf/Evaluate/Static Gradient only.
[9 empty] | 975 | 979 | [7 empty] | Perf 975-979. Swab 156 m3/d @ 90% at 525 m. | Do not run pump until ASP ready.
[18 empty] | SG: 7702 kPa. Ran 64-1200, 73mm, RP25mm. | NOTE ONLY: Pay thickness is 971-986m.
P | 03/5-21 | DONE | Prod |  | 1) Spud Dec 3 5A-21 $312K | 5A |  | Dec 15-21, 2005 (5) | 976 | 981 | Future lower perf potential | V | 5.5 |  |  |  |  | $120K Swabbed 69 m3/d at ~10%, 735m, gassy. Perf only. | Perf/Evaluate/Static Gradient only.
[5 empty] | Cored | [12 empty] | SG: 6666 kPa, 30 deg C. Ran 16-1200, 73mm, 22mm. | Dec 20: Run 16-1200, 73mm tbg, 22mm rods.
P | 03/12-21 | DONE | Prod |  | 3) Spud Dec 16 12B-21 $292K | 12B |  | Jan 16-18, 2006 (3) | 977 | 979 |  | V | 5.5 |  |  |  |  | $83K Swabbed 77 m3/d @ 35%, 700m, 0.5% solids. | Perf/Evaluate/Static Gradient only.
[6 empty] | 12B |  | May 14-15, 2006 (2) | [9 empty] | SG: 6209 kPaa. Ran 32-1200, 73mm, 22mm. | Do not run pump until ASP ready.
P | 03/06-16 | WO Drilling | WO P/L |  | 6A-16 To be cored | 12B | [5 empty] | V | 5.5
|  | (July 2006) |  |  | Replaces Reentry of 2/6-16 | 12B