## Cur Producers List 10-7-05
Warner ASP - Producing Oil Well Downhole Work
June 26, 2006 - Note that rates/FL for middle and bottom wells are original fall 2005 numbers | [13 empty] | June 12
v3.7 | [13 empty] | 2006
|  | Rig Up | Recommended Perf Intervals for ASP |  |  |  | Old GLCC Perfs | Recommendation | V/Dir | Frac | Csg | Current | Current | Target
|  | Status | Fr mSS | To mSS | mKB MD | mKB MD | mKB MD |  |  | Y/N | " | O/F m3/d | JTF/JIH | m3/d | Comments
Perf New Interval (1m or more) | [9 empty] | *** Updated rates/FLs June 25, 2006 ***
1 | 00/03-09 | DHF or | -45 | -46.5 | 991 | 992.5 | 978.1-978.7,979.6-979.9,981.5-983.6,990.9-991.5 | Add perfs | V | Y('74) | 4.5 | 0.6/4.6 | 89/104 | 25 | Declined | New perfs
July
2 | 03/08-20 | WO Rig | -52 | -56 | 980 | 984 | 980.0-982.0 | Add perfs | V | N | 5.5 | 0.8/25 | 100/102 | 50 | No decline | 2" Insert in hole since 1997; 6.5spm, 84".
3 | 02/15-20 | DHF or | -56.5 | -59 | 1005.5 | 1008 | 1013.0-1015.0,1010.5-1012.0 | Add perfs | Dir | N | 5.5 | 10.6/88 | 75/106 | 75 | Oil cut increasing on June 22, 2006!!! | Top perfs are separate interval.
|  | July | -61 | -62.5 | 1010 | 1011.5
|  |  | -63.5 | -67 | 1012.5 | 1016
4 | 03/06-29 | Delay | -62.5 | -70 | 1006.5 | 1014 | 1006.5-1009.0,1011.0-1012.5 | Add perfs | Dir | Y | 5.5 | 1.7/168 | 60/105 | 125 | Declined | Rate over 100 m3/d
Top perfs are separate interval.
5 | 02/08-29 | Delay | -56 | -60.5 | 967 | 971.5 | 967-970, 970-972(Frac'd), 973-975(Frac'd) | Add perfs | V | Y | 5.5 | 1.7/21 | 80/102 | 25 | Oil cut increasing on June 18, 2006!!!
|  |  | -62 | -65 | 973 | 976 | 975-976, 977.5-979
|  |  | -66 | -68 | 977 | 980
6 | 00/10-29 | WO Rig | -62.5 | -70 | 974.5 | 980 | 975.4-976.9(CEMSQ), 975.5-977.0(7 spm) | Add perfs | V | N | 4.5 | 0.7/15 | 76/103 | 25
7 | 00/11-29 | DONE | -67.5 | -71 | 973.5 | 977 | 975.1-975.4,975.7-976,976.3-976.3(All CEMSQ) | Old Rate -> | V | N | 4.5 | 1.0/19.4 | 69/104 | 60 | 96 m3/d @ 714m; 80-90%; trace solids. | Upgrade to 16-1200 screw pump.
[7 empty] | 974.1-974.8 (*** 3 spm ***) | Added perfs -> |  |  |  | 0.5/49 | 77/104 |  | PWOP Dec 22. 28-1200, 73mm, 22mm.
8 | 03/15-29 | DONE | ? | ? | 1061 | 1065.5 | 1092.5-1093.5(STTH),CEMBRP 1087.0-1090.0 | Old Rate -> | Dir | Y | 5.5 | 0.5/51 | 87/104 | 25 | $91K 82 m3/d @ 840m; 90%; 0.5% solids.
|  |  | ? | ? | 1068 | 1070.5 | 1060.5-1063.5(Frac'd),1068.0-1069.5(Frac'd) | Added perfs -> |  |  |  | 0.4/44 | 90/104 |  | PWOP. 32-1200, 73mm, 22mm Jake.
Rate Optimization - Reevaluate fall 2006 | [9 empty] | *** Rates/FLs from Fall 2005 ***
1 | 03/02-09 | Delay | -39.5 | -42.5 | 998.5 | 1001.5 | 998.5-1002.0,986.0-987.0,982.0-984.0 | Wait - fall 2006 | Dir | N | 5.5 | 1.4/17 | 87/104 | 50 | No decline | Is rate ok? A vs C (top) - frac A only?
2 | 02/06-09 | Delay | -44 | -47 | 989 | 992 | 980-981.5,989-992,988.5-990,985-987.5,983.0-984 | Wait - fall 2006 | V | N | 5.5 | 0.6/10.7 | 98/104 | 25 | No decline
3 | 00/07-09 | Delay | -34 | -38 | 977 | 981 | 977.2-978.7,980.2-981.2,984.5-989.4, 987.6-989.7 | Wait - fall 2006 | V | N | 4.5 | 0.9/98.4 | 83/104 | 75 | Good Poro | Rate almost 100 m3/d
|  |  | -41.5 | -46.5 | 984.5 | 989.5
4 | 03/11-09 | Delay | -43.5 | -47 | 994.5 | 998 | 994.5-998.0 | Wait - fall 2006 | Dir | N | 5.5 | 1.0/32 | 70/104 | 75 | Declined
5 | 03/14-09 | Delay | -40 | -41.5 | 998 | 999.5 | 998.0-999.5,1005.5-1006.5 | Wait - fall 2006 | Dir | N | 5.5 | 0.7/38 | 70/104 | 50 |  | Is rate ok?
6 | 02/02-16 | Delay until | -32 | -35 | 1000 | 1003 | 966.5-1003.0(SQZ'D),1013.0-1013.3,1005.5-1007.0 | Wait - fall 2006 | Dir | N | 5.5 | 2.2/215 | 63/104 | 125 | Thick Pay, | Add perfs
|  | rate<150m3/d | -37.5 | -42 | 1005.5 | 1010 |  | Add perfs | [6 empty] | Behd CCG Com
[5 empty] | 1011.5 | 1015.5
7 | 00/09-20 | Delay | -58 | -64.5 | 985 | 991.5 | 984.8-986.0,989.7-991.5,986.9-987.2,988.5-988.8 | Wait - fall 2006 | V | Y | 4.5 | 0.7/17 | 61/85 | 50 |  | Rate dropped off when 5-21 stopped injecting.
8 | 00/13-21 | Delay | -62 | -66 | 986 | 990 | 986.3-989.7 | Wait - fall 2006 | V | Y | 4.5 | 1.2/13 | 103/104 | 50 | Inflow too low
9 | 02/06-29 | Delay | -60.9 | -61.6 | 1026.5 | 1027.5 | 1026.5-1027.5,1028.5-1031.0 | Wait - fall 2006 | Dir | N | 5.5 | 1.2/58 | 75/104 | 25 | Declined
|  |  | -62.4 | -64.1 | 1028.5 | 1031
10 | 02/07-29 | Delay | -66.2 | -68.2 | 1042.5 | 1045 | 1042.5-1045.0 | Wait - fall 2006 | Dir | N | 5.5 | 1.2/49 | 66/104 | 75 | Declined
11 | 04/10-29 | Delay | -56.4 | -59.4 | 1029.5 | 1033 | 1029.5-1034.0(13 spm) | Wait - fall 2006 | Dir | Y | 5.5 | 1.0/96 | 87/104 | 100
|  |  | -60.3 | -63.3 | 1034 | 1037.5 |  | Add perfs
12 | 02/11-29 | Delay | -62 | -63.3 | 1019 | 1020.5 | 1018.5-1021.0,1022.5-1025.5,1027.0-1027.0 | Wait - fall 2006 | Dir | N | 5.5 | 1.2/29.5 | 80/104 | 60
|  |  | -65.1 | -67.4 | 1022.5 | 1025
13 | 00/13-29 | Delay | -63.2 | -65.3 | 1041.5 | 1044 | 1061.5-1063(STTH),CEMBRP 1052-1060,1041-1044 | Wait - fall 2006 | Dir | N | 5.5 | 1.1/35 | 62/104 | 30
No Prod Opt Required | [9 empty] | *** Rates/FLs from Fall 2005 ***
1 | 02/02-09 | OK |  |  |  |  | 997.0-1001.0,1008.0-1010.0 | None | Dir | Y | 5.5 | 1.0/52.1 | 75/104 | 100 | No decline
2 | 02/07-09 | OK |  |  |  |  | 989.0-992.0,979.0-989.4 | None | V | N | 5.5 | 2.6/134 | 90/104 | 75 | NO Larry's Log
3 | 00/10-09 | OK - ESP |  |  |  |  | 982.4-984.8,988.2-989.4,985.7-989.1 | None | V | N | 4.5 | 2.2/233 | 94/104 | 75 | Good Poro
4 | 00/15-09 | OK |  |  |  |  | 986.6-988.5,979.0-986,977.8-978.4,976.3-977.2 | None | V | Y | 4.5 | 2.3/245 | 40/62 | 150 | Good, Blocky | Need to run tbg lower?
5 | 00/16-20 | OK |  |  |  |  | 979.9-981.2,981.8-986.6,987.6-991.2,BP@960 | None | V | Y | 4.5 | 3.2/319 | 54/104 | 100
6 | 02/16-20 | OK |  |  |  |  | 994.0-996.0 | None | Dir |  | 5.5 | 4.5/303 | 56/104 | 100 | No Intp'd logs
7 | 00/02-29 | OK - ESP |  |  |  |  | 979.6-981.5,983.3-986.9,989.1-992.1 | None | Dir | N | 5.5 | 2.7/177 | 91/104 | 75 | Watch TVD/MD
8 | 00/07-29 | OK - ESP |  |  |  |  | 977.8-979.0,980.2-981.5,982.7-983.9 | None | V | N | 4.5 | 1.1/114 | 78/104 | 50 |  | Rate over 100 m3/d; 64 HZ ESP
Total: